## Worksheet
Phase | Start Date | End Date | Responsible Team | Status
Market Research & Analysis | 2024-01-05 | 2024-01-19 | Research & Insights | In Progress
Target Audience Definition | 2024-01-20 | 2024-01-31 | Marketing Strategy | Pending
Content & Campaign Development | 2024-02-01 | 2024-02-15 | Content Team | Pending
Digital Campaign Launch (Social, Email) | 2024-02-16 | 2024-03-15 | Digital Marketing | Pending
Event & Offline Promotion | 2024-03-01 | 2024-03-31 | Events & PR | Pending
Performance Tracking & Reporting | 2024-04-01 | 2024-04-30 | Data Analytics | Pending
Post-Campaign Review & Optimization | 2024-05-01 | 2024-05-15 | Marketing Leadership | Pending