## Worksheet
Task ID | Task Description | Start Date | End Date | Status | Responsible Team/Person
MKT-001 | Market Research & Analysis | 2024-01-05 | 2024-01-19 | In Progress | Market Insights Team
MKT-002 | Competitor Benchmarking | 2024-01-15 | 2024-01-31 | To Do | Data Analytics Group
MKT-003 | Target Audience Segmentation | 2024-01-22 | 2024-02-15 | To Do | Marketing Strategy Team
MKT-004 | Create Campaign Concept & Messaging | 2024-02-16 | 2024-03-15 | To Do | Creative Team
MKT-005 | Content Creation (Digital & Print) | 2024-03-16 | 2024-04-30 | To Do | Creative & Copywriting Team
MKT-006 | Media Planning & Placement Strategy | 2024-03-16 | 2024-04-30 | To Do | Media Buying Team
MKT-007 | Campaign Launch Preparation | 2024-05-01 | 2024-05-15 | To Do | Project Coordination Team
MKT-008 | Campaign Launch (Go Live) | 2024-05-16 | 2024-05-16 | To Do | All Teams
MKT-009 | Performance Monitoring & KPI Tracking | 2024-05-17 | 2024-08-31 | To Do | Data & Analytics Team
MKT-010 | Post-Campaign Review & Reporting | 2024-09-01 | 2024-09-30 | To Do | Marketing Leadership Team
Note:This table is a template for marketing planning and project timeline tracking. Update status, dates, and responsibilities as needed during campaign execution.