## Worksheet
Task ID | Task Description | Start Date | End Date | Status | Assigned To | Dependencies
Phase 1: Research & Strategy (Weeks 1-4)
T01 | Market Analysis and Competitor Research | 2023-08-28 | 2023-09-15 | In Progress | Jane Smith, Market Analyst | N/A
T02 | Customer Persona Development | 2023-09-16 | 2023-09-29 | To Do | Mark Johnson, UX Researcher | T01 Complete
T03 | Marketing Goals and KPIs Setting | 2023-09-30 | 2023-10-15 | To Do | Lisa Chen, Marketing Director | T02 Complete, T01 Complete
Phase 2: Content & Creative Development (Weeks 5-8)
T04 | Content Strategy Outline Creation | 2023-10-16 | 2023-10-31 | To Do | Derek Lee, Content Strategist | T03 Complete
T05 | Design Mockups for Digital Campaigns | 2023-11-01 | 2023-11-17 | To Do | Sarah Kim, Creative Director | T04 Complete, T03 Complete
T06 | Copywriting for Email and Social Media Campaigns | 2023-11-18 | 2023-12-05 | To Do | Alex Rivera, Copywriter | T04 Complete, T05 Complete
Phase 3: Campaign Execution (Weeks 9-12)
T07 | Launch Email Marketing Campaign | 2023-12-06 | 2023-12-15 | To Do | Lisa Chen, Marketing Director | T06 Complete, T05 Complete, T04 Complete
T08 | Run Paid Social Media Ads (Facebook & Instagram) | 2023-12-16 | 2024-01-15 | To Do | Nina Patel, Digital Ads Manager | T05 Complete, T06 Complete, T07 Complete
Phase 4: Monitoring & Reporting (Weeks 13-16)
T09 | Weekly Performance Reports and Dashboard Updates | 2024-01-16 | 2024-01-31 | To Do | Jane Smith, Market Analyst | T07 Complete, T08 Complete
Phase 5: Review & Optimization (Weeks 17-20)
T10 | Final Marketing Campaign Review Meeting | 2024-02-01 | 2024-02-15 | To Do | Lisa Chen, Marketing Director | T09 Complete, T08 Complete, T07 Complete
Overall Project Timeline: 20 Weeks (From 2023-08-28 to 2024-02-15)