## Worksheet
Task | Owner | Timeline (Start to End) | [5 empty] | Progress
|  | Q1 Jan-Feb | Q1 Mar | Q2 Apr-May | Q2 (Jun) | Q3 (Jul-Aug) | Q3 (Sep-Oct)
Market Research & Analysis | Jane Doe | ● | ● |  |  |  |  | 35%
Brand Positioning & Messaging | Mike Smith | ● | ● | ● |  |  |  | 60%
Content Creation (Video, Copy) | Sarah Lee |  | ● | ● | ● |  |  | 75%
Social Media Campaign Launch | Chris Brown |  |  | ● | ● | ● |  | 85%
Email Marketing Series | Lisa Wang |  |  | ● | ● | ● |  | 85%
Event & Webinar Planning | Daniel Park |  |  |  | ● | ● | ● | 78%
Performance Tracking & Reporting | Amanda Gray |  |  | ● | ● | ● | ● | 92%
Final Strategy Review & Optimization | Jane Doe |  |  |  |  | ● | ● | 88%
Overall Status |  | 83% Complete | [5 empty] | 87%