## Worksheet
Marketing Planning - Project Timeline
Phase | Activity | Start Date | End Date | Status | Responsible Team/Person
Planning Phase | Market Research & Analysis | 2024-01-05 | 2024-01-19 | In Progress | Market Intelligence Team
| Objective & KPI Setting | 2024-01-20 | 2024-01-31 | Pending | Marketing Director
Strategy Development | Target Audience Segmentation | 2024-02-01 | 2024-02-15 | Pending | Data Analytics Unit
| Channel Strategy Design | 2024-02-16 | 2024-03-01 | Pending | Campaign Strategists
| Marketing Mix (4Ps) Finalization | 2024-03-02 | 2024-03-15 | Pending | Marketing Team Lead
Creative Development | Content Creation (Copy & Visual) | 2024-03-16 | 2024-04-15 | Pending | Creative Studio
| Ad Design & Production | 2024-04-16 | 2024-05-15 | Pending | Design Team
| Approval & Iteration Cycles | 2024-05-16 | 2024-05-31 | Pending | Multidisciplinary Review Board
Execution Phase | Launch Campaign (Omnichannel) | 2024-06-01 | 2024-07-31 | Pending | Campaign Management Team
| Performance Monitoring & Optimization | 2024-06-15 | 2024-08-31 | Pending | Data Analysts & Performance Marketers
Evaluation & Reporting | Monthly Performance Review (Q2) | 2024-07-01 | 2024-07-31 | Pending | KPI Task Force
| Post-Campaign Report & Recommendations | 2024-08-01 | 2024-08-31 | Pending | Marketing Analytics Team
Project Summary
Overall Project Duration: |  | January 5, 2024 – August 31, 2024
Total Phases: |  | 6
Active Tasks: |  | 15 / 18
Status Summary: |  | 3 Pending,1 In Progress,14 Completed