## Worksheet
Marketing Planning - Project Timeline (Manager View)
Phase / Task | Start Date | End Date | Status | Budget Allocated ($) | Owner
Market Research & Analysis | 2024-01-15 | 2024-01-31 | Completed | 8,500 | Jane Doe
Target Audience Definition | 2024-02-01 | 2024-02-15 | Completed | 6,000 | John Smith
Brand Positioning Strategy | 2024-02-16 | 2024-03-15 | Ongoing | 15,000 | Sarah Johnson
Content Creation (Digital & Print) | 2024-03-16 | 2024-05-31 | Ongoing | 45,000 | Mike Brown
Social Media Campaign Launch | 2024-04-15 | 2024-11-30 | Ongoing | 60,000 | Lisa Wang
Email Marketing Series | 2024-05-15 | 2024-11-30 | Delayed | 30,000 | Tom Anderson
Influencer Partnership Agreements | 2024-06-15 | 2024-12-31 | Ongoing | 55,000 | Emily Clark
Event & Webinar Planning (Q3) | 2024-07-15 | 2024-11-30 | Ongoing | 35,000 | Nathan Reed
Performance Analytics & Reporting (Monthly) | 2024-01-31 | 2024-12-31 | Ongoing | 75,000 | Allison Lee
Total Project Budget:$334,500 ¦Current Status:Ongoing (1 out of 9 tasks delayed)