## Worksheet
Phase | Task | Start Date | End Date | Status
Research & Planning | Market Analysis & Competitor Research | 2024-01-01 | 2024-01-15 | In Progress
Research & Planning | Define Target Audience Segments | 2024-01-16 | 2024-01-31 | Pending
Strategy Development | Create Marketing Objectives & KPIs | 2024-02-01 | 2024-02-15 | Pending
Strategy Development | Develop Brand Messaging & Positioning | 2024-02-16 | 2024-03-01 | Pending
Campaign Execution | Launch Email Marketing Campaign | 2024-03-15 | 2024-04-15 | Pending
Campaign Execution | Run Social Media Ads (Platform A) | 2024-03-15 | 2024-05-31 | Pending
Campaign Execution | Run Social Media Ads (Platform B) | 2024-04-01 | 2024-06-30 | Pending
Campaign Execution | Host Webinar: Product Introduction | 2024-05-15 | 2024-05-31 | Pending
Reporting & Optimization | Analyze Campaign Performance (Monthly) | 2024-04-01 | 2024-12-31 | Pending
Reporting & Optimization | Adjust Strategies Based on Data Insights | 2024-05-01 | 2024-12-31 | Pending