## Worksheet
Marketing Planning - Project Timeline
Startup Style Template ¦ Q3 2024
Phase | Task Name | Start Date | End Date | Status | Budget (USD)
Phase 1: Research & Discovery
1.1 | Market Analysis & Competitor Research | 2024-07-01 | 2024-07-15 | In Progress | $3,500
1.2 | Customer Persona Development | 2024-07-16 | 2024-07-31 | Pending | $2,800
Phase 2: Strategy & Planning
2.1 | Marketing Objectives & KPIs Definition | 2024-08-01 | 2024-08-15 | Pending | $1,500
2.2 | Channel Strategy & Budget Allocation | 2024-08-16 | 2024-08-31 | Pending | $4,000
Phase 3: Content & Creative Development
3.1 | Brand Messaging & Positioning | 2024-09-01 | 2024-09-15 | Pending | $3,800
3.2 | Visual Identity & Design Assets Creation | 2024-09-16 | 2024-09-30 | Pending | $5,500
Phase 4: Campaign Launch
4.1 | Digital Ad Campaign (Social & Search) | 2024-10-01 | 2024-10-31 | Pending | $8,500
4.2 | Email Marketing & Newsletter Series | 2024-10-15 | 2024-11-30 | Pending | $3,200
Phase 5: Measurement & Optimization
5.1 | Performance Tracking & Reporting | 2024-10-01 | 2024-11-30 | Pending | $3,750
5.2 | A/B Testing & Conversion Optimization | 2024-11-01 | 2024-11-30 | Pending | $3,950
Total Estimated Budget:$50,500
Project Duration: July 1st – November 30th, 2024