## Worksheet
Marketing Planning - Project Timeline (Summary View)
Phase | Key Activities | Start Date | End Date | Status | Responsible Team
Planning & Strategy Phase
Market Research | Conduct surveys, competitor analysis, customer segmentation | 2023-10-01 | 2023-10-15 | In Progress | Research Team
Objective Setting | Define KPIs, SMART goals, and campaign objectives | 2023-10-16 | 2023-10-20 | Pending | Marketing Manager
Campaign Development Phase
Content Creation | Develop creative assets, copywriting, video production | 2023-10-21 | 2023-11-05 | Pending | Creative Team
Channel Planning | Select and schedule media channels (social, email, display) | 2023-10-25 | 2023-11-10 | Pending | Media Team
Launch & Execution Phase
Pre-Launch Campaigns | Teaser content, countdowns, early access promotions | 2023-11-11 | 2023-11-20 | Pending | Marketing Team
Main Campaign Launch | Deploy full campaign across all channels, real-time monitoring | 2023-11-21 | 2023-12-15 | Pending | All Teams
Review & Optimization Phase
Performance Analysis | Collect data, measure KPIs, report insights | 2023-12-16 | 2023-12-31 | Pending | Analytics Team
Total Duration: 90 Days (October 1 - December 31, 2023)
Prepared on: