## Worksheet
Marketing Planning - Project Timeline (Team Use)
Phase | Task | Owner | Start Date | End Date | Status | Notes/Comments(Team Collaboration)
Planning Phase | Market Research & Analysis | Marketing Team Lead | 2024-04-01 | 2024-04-15 | In Progress | Preliminary data collection underway.Team input requested by 2024-04-13.
| Objective & KPI Setting | Marketing Strategy Manager | 2024-04-16 | 2024-04-25 | Pending Review | KPIs to be approved by stakeholders.Team feedback due 2024-04-19.
Execution Phase | Campaign Creative Development | Design Team | 2024-04-26 | 2024-05-15 | Not Started | Assets to be reviewed in weekly sync.Awaiting content brief by 2024-04-30.
| Channel Strategy & Scheduling | Digital Marketing Specialist | 2024-05-16 | 2024-05-31 | Not Started | Publishing calendar to be shared by 2024-05-18.Team alignment meeting scheduled.
| Campaign Launch & Monitoring | Marketing Operations | 2024-06-01 | 2024-06-30 | Not Started | Daily performance tracking begins.Bi-weekly team reviews planned.
Review Phase | Performance Analysis & Reporting | Data Analyst | 2024-07-01 | 2024-07-15 | Not Started | FYI: Include social, web, and email metrics.Team input required by 2024-07-13.
| Lessons Learned & Next Steps | Project Manager | 2024-07-16 | 2024-07-31 | Not Started | Team workshop scheduled on 2024-07-31.Draft report due 2024-07-31.
Template for Team Use – Last Updated: April 2024