## Worksheet
Marketing Planning - Project Timeline Template Version
Phase | Task | Start Date | End Date | Responsible Team/Person | Status
Planning & Research | MKT-01: Market Analysis & Competitor Review | 2024-04-01 | 2024-04-15 | Market Research Team | In Progress
Planning & Research | MKT-02: Target Audience Segmentation | 2024-04-16 | 2024-04-30 | Customer Insights Team | Pending
Strategy Development | MKT-03: Marketing Goals & KPIs Definition | 2024-05-01 | 2024-05-10 | Marketing Strategy Lead | Pending
Strategy Development | MKT-04: Campaign Theme & Messaging Finalization | 2024-05-11 | 2024-05-20 | Creative Team | Pending
Content Creation | MKT-05: Content Calendar Development | 2024-05-21 | 2024-06-10 | Content Team | Pending
Content Creation | MKT-06: Design & Copywriting Production | 2024-05-21 | 2024-06-15 | Creative Team & Copywriters | Pending
Execution & Launch | MKT-07: Campaign Launch (Phase 1) | 2024-06-16 | 2024-06-30 | Digital Marketing Team | Pending
Execution & Launch | MKT-08: Social Media & Email Campaigns Live | 2024-06-16 | 2024-07-31 | Social Media & Email Team | Pending
Monitoring & Optimization | MKT-09: Performance Tracking & Weekly Reviews | 2024-07-01 | 2024-08-31 | Analytics Team | Pending
Evaluation & Reporting | MKT-10: Final Campaign Report & ROI Analysis | 2024-09-01 | 2024-09-15 | Marketing Director & Analysts | Pending
Notes: This timeline is based on Template Version 1.2. Adjust dates and resources as needed.