## Worksheet
Task ID | Task Description | Start Date | End Date | Responsible Team | Status | % Complete
MKT-001 | Market Research & Analysis | 2023-10-01 | 2023-10-15 | Research Team | In Progress | 65%
MKT-002 | Competitor Benchmarking (Milestone) | 2023-10-16 | 2023-10-18 | Strategy Team | Completed | 100%
MKT-003 | Target Audience Segmentation | 2023-10-19 | 2023-10-25 | Data Analytics Team | In Progress | 45%
MKT-004 | Marketing Strategy Draft (Milestone) | 2023-10-26 | 2023-10-31 | Marketing Team | Pending Review | 85%
MKT-005 | Content Creation (Blogs, Videos) | 2023-11-01 | 2023-11-15 | Content Team | Not Started | 0%
MKT-006 | Launch Campaign Approval (Milestone) | 2023-11-16 | 2023-11-20 | Executive Team | Pending Review | 0%
MKT-007 | Channel Deployment (Social, Email, SEO) | 2023-11-21 | 2023-12-05 | Digital Marketing Team | Not Started | 0%
MKT-008 | Full Campaign Launch (Milestone) | 2023-12-06 | 2023-12-06 | All Teams | Pending | 0%
MKT-009 | Performance Monitoring & Reporting | 2023-12-07 | 2024-01-31 | Analytics Team | Not Started | 0%
Legend:
Yellowindicates a milestone task.
Status values: Not Started, In Progress, Pending Review, Completed.