## Worksheet
Daily Marketing Planning Project Tracker
Task ID | Task Description | Assigned To | Start Date | Due Date | Status | Daily Update (DD/MM/YYYY)
#MKT-001 | Create Q3 Social Media Content Calendar | Jane Doe | 01/07/2024 | 31/07/2024 | In Progress | Content draft finalized. Review scheduled.
#MKT-002 | Design Email Newsletter Template | Mike Smith | 02/07/2024 | 15/07/2024 | In Progress | Initial wireframe approved. Finalizing design.
#MKT-003 | Conduct Competitor Analysis Report | Lisa Wong | 03/07/2024 | 10/07/2024 | Completed | Report submitted and shared with team.
#MKT-004 | Set Up Google Ads Campaigns | Tom Reed | 05/07/2024 | 18/07/2024 | Pending | Waiting for budget approval.
#MKT-005 | Host Live Webinar on New Product Launch | Sarah Lee | 10/07/2024 | 14/07/2024 | In Progress | Invitations sent. Speaker briefing completed.
#MKT-006 | Finalize Influencer Partnership Contracts | Alex Chen | 08/07/2024 | 12/07/2024 | Pending | Waiting for legal review.