## Worksheet
MARKETING PLANNING - PROJECT TRACKER (EXTENDED)
Project ID | Project Name | Marketing Objective | Target Audience | Scheduled Start Date | Scheduled End Date | Actual Start Date | Actual End Date | Status | Budget (USD) | Spent (USD) | Remaining Budget (USD) | Owner | Milestones & Progress
PJ001 | Q4 Product Launch Campaign | Increase brand awareness by 35% and generate 2,500 leads. | Millennials (25-40), Urban Professionals | 2023-10-01 | 2023-12-31 | 2023-10-05 | - | In Progress | 75,000.00 | 48,256.75 | 26,743.25 | Sarah Chen | Market Research Complete (Oct 1-10) Creative Assets Finalized (Oct 15) Email Campaign Drafted (Oct 20)
PJ002 | Social Media Engagement Drive | Boost social media engagement rate by 50% across platforms. | Gen Z (18-24), Tech Enthusiasts | 2023-11-01 | 2024-01-31 | 2023-11-05 | - | In Progress | 35,000.00 | 9,876.44 | 25,123.56 | James Wilson | Campaign Strategy Defined (Nov 1-7) Influencer Contracts Signed (Nov 10) Content Calendar Approved (Nov 14)
PJ003 | Email Marketing Series: Onboarding Journey | Improve user onboarding conversion by 25% over 3 months. | First-time App Users | 2023-12-01 | 2024-03-31 | 2024-01-15 | - | Delayed - Review Required | 50,000.00 | 7,634.89 | 42,365.11 | Lisa Park | User Journey Mapping (Dec 1-5) Initial Emails Drafted (Dec 20) Testing Phase Delayed Due to Tech Issues
PJ004 | Trade Show Participation: Global Tech Expo 2024 | Showcase new product line and collect 500 qualified leads. | Industry Partners, Investors, Media | 2024-03-15 | 2024-03-18 | - | - | In Progress (Planning) | 95,000.00 | 34,127.56 | 60,872.44 | Ryan Thompson | Booth Design Approved (Oct 31) Marketing Materials Ready (Dec 15) Sales Team Training Scheduled (Feb 10)
Overall Project Status Summary |  |  |  | Total Projects: 4 ¦ Completed: 0 ¦ In Progress: 3 ¦ Delayed: 1 Total Budget Allocated: $255,000.00 ¦ Total Spent: $99,895.64 ¦ Remaining Budget: $155,104.36