## Worksheet
Project ID | Project Name | Initiator | Status | Priority | Budget (USD) | Lead Manager < t h > Key Deliverables< t h > Risk Level | Notes / Comments
In Progress < t d class="priority-high">High25,000 < t d > 2024-10-01 < t d > 2024-11-30 < t d >High < t d > Increased content volume required; team bandwidth tight.
< t d > MP-002Pending < t d class="priority-medium">Medium18,500 < t d > 2024-11-05 < t d > 2024-12-31 < t d >CRM integration, campaign templates, A/B testing plan < t d class="risk-level-medium">Medium < t d > Approval delay on third-party API access.
< t d > MP-003Completed < t d class="priority-high">High42,000 < t d > 2024-08-15 < t d > 2024-08-31 < t d > 2024-08-31 | 100Event platform, invite list, speaker coordination, post-event survey < t d class="risk-level-low">Low < t d > Smooth execution; positive feedback received.
MP-004In Progress < t d class="priority-high">High | 75,000 < t d > 2024-10-15 < t d > 2025-03-31 < t d >Logo redesign, brand guidelines, asset library update < t d class="risk-level-high">High < t d > Design team delays affecting milestones.
MP-005Pending < t d class="priority-medium">Medium | 12,000 < t d > 2025-01-15 < t d > 2025-04-30 < t d >Keyword research, content audit, pillar pages development < t d class="risk-level-low">Low < t d > Wait for analytics access from IT.