## Worksheet
Marketing Planning - Project Tracker (Planning View)
Task ID | Task Title | Owner | Start Date | End Date | Status | Budget (USD)
MKT-001 | Market Research & Competitor Analysis | Sarah Johnson | 2024-04-01 | 2024-04-15 | In Progress | $3,500
MKT-002 | Target Audience Segmentation | David Chen | 2024-04-16 | 2024-04-30 | Pending | $2,800
MKT-003 | Brand Positioning & Messaging Framework | Lisa Ramirez | 2024-05-01 | 2024-05-15 | Pending | $4,200
MKT-004 | Content Calendar Development (Q2) | James Wilson | 2024-05-16 | 2024-06-30 | Pending | $5,100
MKT-005 | Launch Campaign Design (Digital & Print) | Emma Brown | 2024-06-15 | 2024-07-31 | Pending | $18,900
MKT-006 | PR & Media Outreach Strategy | Marcus Lee | 2024-07-01 | 2024-07-31 | Pending | $6,500
MKT-007 | Performance Metrics & KPI Setup | Sophia Patel | 2024-08-01 | 2024-08-15 | Pending | $3,750
Total Budget: | [5 empty] | $44,750