## Worksheet
Task ID | Project Phase | Task Description | Assigned To | Status | Start Date | End Date | Budget (USD)
TASK001 | Planning | Define campaign goals and KPIs | Alice Johnson | Not Started | 2024-04-01 | 2024-04-15 | $5,000
TASK002 | Research | Conduct market and audience analysis | Bob Smith | In Progress | 2024-04-16 | 2024-05-15
TASK003 | Content Creation | Create social media visuals and copy | Carol Lee | In Progress | 2024-05-16 | 2024-06-15
TASK004 | Promotion | Launch paid advertising campaigns | Dave Brown | Not Started | 2024-06-16 | 2024-07-31
TASK005 | Analysis & Reporting | Analyze campaign performance and deliver report | Eve White | Not Started | 2024-08-01 | 2024-08-15