## Worksheet
Marketing Planning - Project Tracker (Startup)
Task ID | Task Name | Owner | Start Date | Due Date | Status | Budget (USD)
MTK-001 | Market Research & Competitor Analysis | Alice Johnson | 2024-03-15 | 2024-03-31 | In Progress | $850
MTK-002 | Brand Positioning & Messaging Development | Bob Smith | 2024-03-18 | 2024-04-15 | Pending | $1,500
MTK-003 | Content Calendar (Q2) | Carol Davis | 2024-04-01 | 2024-05-15 | Pending | $750
MTK-004 | Social Media Campaign Launch (Phase 1) | David Lee | 2024-04-10 | 2024-05-31 | Pending | $3,800
MTK-005 | Email Marketing Funnel Setup | Eva Martinez | 2024-04-15 | 2024-06-30 | Pending | $1,950
MTK-006 | Product Launch Event Planning | Frank Wilson | 2024-05-20 | 2024-07-15 | Pending | $6,500
Total Project Budget:$15,350