## Worksheet
Marketing Planning - Weekly Project Tracker (Weekly)
Week Starting | Project Name | Objective | Key Activities | Status | Owner(s) | Estimated Effort (hrs) | Budget Allocated ($) | Milestones / Deliverables | Notes
2023-10-02 | Social Media Campaign Q4 | Increase brand engagement by 30% in Q4 | Create content calendar, design graphics, schedule posts | In Progress | Jane Doe, Mark Lee | 40 | 2500 | Weekly content calendar approved by Oct 15; first post scheduled for Oct 18 | Needs approval on campaign visuals from legal team.
2023-10-02 | Email Newsletter Series | Drive repeat customer engagement through segmented emails | Segment audience, write copy, design templates | Pending | Lisa Chen | 25 | 1200 | Email draft review scheduled for Oct 10; launch planned for Oct 25 | Waiting on customer data from CRM team.
2023-10-09 | Influencer Outreach - Fall Collection | Secure 5 influencer partnerships for new product launch | Identify influencers, outreach emails, negotiation | Completed | Tom Wilson | 30 | 5000 | 5 signed agreements confirmed; content delivery timeline set. | All contracts finalized and filed.
2023-10-16 | Website SEO Optimization | Improve organic search rankings for key service pages | Keyword research, meta tags update, content optimization | In Progress | Alex Rivera | 50 | 3000 | On-page SEO audit completed; first round of updates implemented. | Monitoring traffic changes post-update.
2023-10-23 | Q4 Budget Planning Workshop | Finalize marketing budget allocation for Q4 | Schedule meeting, collect inputs, present draft budget | Pending | Emma Taylor, John Park | 15 | 0 (Internal) | Meeting scheduled for Oct 30; draft budget due Nov 2. | Requires input from all team leads.
Weekly Summary: 5 Projects ¦ In Progress: 2 ¦ Completed: 1 ¦ Pending: 2