## Worksheet
Marketing Planning - Advanced Schedule Planner
Phase / Task | Timeline |  |  |  | Owner | Status | Progress
| Start Date | End Date | Due Date (Milestone) | Duration (Days)
Phase 1: Market Research & Strategy Development
Market Analysis (Primary & Secondary) | 2024-01-05 | 2024-01-19 | 2024-01-19 | 15 | Marketing Analytics Team | Completed
Competitor Benchmarking | 2024-01-15 | 2024-01-31 | 2024-01-31 | 17 | Competitor Intelligence Lead | Completed
Phase 2: Campaign Strategy & Creative Development
Campaign Objective Setting | 2024-02-01 | 2024-02-15 | 2024-02-15 | 15 | Marketing Director | Completed
Creative Concept Development | 2024-02-15 | 2024-03-15 | 2024-03-15 | 30 | Creative Team Lead | Ongoing
Phase 3: Channel Setup & Resource Allocation
Digital Platform Configuration | 2024-03-16 | 2024-03-31 | 2024-03-31 | 16 | IT & Digital Ops Team | Ongoing
Media Buy Planning & Approval | 2024-03-15 | 2024-04-15 | 2024-04-15 | 31 | Media Strategist | Delayed
Phase 4: Campaign Launch & Performance Tracking
Campaign Launch (Day 1) | 2024-04-16 | 2024-05-31 | 2024-04-16 | 46 | Marketing Manager | Ongoing
Weekly Performance Review | 2024-04-16 | 2024-05-31 | Every Monday | 7 (Recurring) | Analytics Team | Completed
Phase 5: Campaign Optimization & Final Report
Mid-Campaign Adjustments | 2024-04-16 | 2024-05-15 | 2024-05-15 | 30 | Data Analysts & Marketers | Completed
Final Performance Report & Retrospective | 2024-05-16 | 2024-05-31 | 2024-05-31 | 16 | Marketing Director & PMO | Delayed