## Worksheet
Task | Start Date | End Date | Assigned To | Status | Priority
Market Research & Analysis | 2024-01-05 | 2024-01-15 | Jane Doe | In Progress | High
Competitor Analysis | 2024-01-16 | 2024-01-25 | John Smith | Pending | Medium
Create Campaign Strategy | 2024-01-26 | 2024-02-05 | Jane Doe | Pending | High
Design Marketing Materials | 2024-02-06 | 2024-02-15 | Maria Lopez | Pending | Medium
Develop Social Media Content Calendar | 2024-02-16 | 2024-03-05 | David Kim | Pending | High
Launch Campaign Phase 1 | 2024-03-06 | 2024-03-15 | All Team Members | Pending | High
Analyze Results & Optimize Campaign | 2024-03-16 | 2024-03-31 | Jane Doe, John Smith | Pending | Medium