## Worksheet
Date | Activity | Responsible | Status | Notes
2024-01-05 | Market Research Phase 1 | Marketing Team A | Planned
2024-01-10 | Competitor Analysis Report | Analytics Lead | In Progress | Updated data from Q4 2023.
2024-01-15 | Target Audience Segmentation | Segmentation Specialist | Planned
2024-01-20 | Content Strategy Workshop | Marketing Director | Scheduled | Internal team only.
2024-01-25 | Campaign Concept Draft | Content Team | Pending | Review feedback needed.
2024-01-30 | Initial Campaign Approval | Marketing Manager | Planned
2024-02-05 | Design Assets Creation | Graphic Designers | Planned
2024-02-10 | Ad Copy Finalization | Copywriters | Pending | Based on design input.
2024-02-15 | Testing Phase (A/B) | Marketing Analysts | Planned
2024-02-18 | Campaign Launch (Soft) | Entire Marketing Team | Planned
2024-02-25 | Performance Review Meeting | Marketing Director | Pending | Post-launch evaluation.
Marketing Planning Schedule - Compact Version ¦ Updated: April 2024