## Worksheet
Marketing Planning Dashboard Schedule
Quarterly Campaign Strategy & Execution Tracker (Q3 2024)
Activity | Start Date | End Date | Owner | Status | Budget (USD) | KPI Target
Market Research & Analysis | 2024-07-01 | 2024-07-15 | Jane Doe (Marketing Lead) | Active | $8,500 | Survey 500+ customers
Brand Positioning Strategy | 2024-07-16 | 2024-07-31 | Mark Taylor (Strategy) | Pending | $15,000 | Updated positioning document ready
Social Media Campaign Launch | 2024-08-01 | 2024-11-30 | Sarah Kim (Digital Marketing) | Active | $65,000 | Reach 5M impressions ¦ 8% engagement rate
Email Marketing Series (Q3) | 2024-08-15 | 2024-10-31 | David Chen (Content Team) | Active | $7,500 | Open rate > 45% ¦ CTR > 6%
Webinar Series: Product Insights | 2024-09-10 | 2024-10-15 | Linda White (Events) | Pending | $18,750 | Register 300+ attendees per session
Trade Show Participation (TechConf) | 2024-10-25 | 2024-10-27 | Ryan Patel (Events & PR) | Pending | $45,000 | Collect 150+ qualified leads
Post-Campaign Review & Reporting | 2024-11-20 | 2024-12-05 | Jane Doe (Marketing Lead) | Pending | $6,300 | Comprehensive performance report delivered