## Worksheet
Marketing Planning Schedule Planner (Detailed)
Phase | Task | Sub-Task | Responsible Team | Start Date | End Date | Status | Priority Level
Phase 1: Research & Analysis | Market Research | Conduct competitor analysis | Marketing Analytics Team | 2023-10-01 | 2023-10-15 | In Progress | High
| Phase 1: Research & Analysis | Customer Persona Development | Define target audience segments | Customer Insights Team | 2023-10-05 | 2023-10-18 | In Progress | High
|  |  | Validate persona assumptions through surveys | Customer Insights Team | 2023-10-16 | 2023-10-25 | Pending | Medium
|  |  | Conduct focus group sessions (x3) | Customer Research Team | 2023-10-20 | 2023-11-05 | Pending | High
Phase 2: Strategy Development |  | Marketing Strategy Formulation | Create overarching campaign framework | Marketing Strategy Team | 2023-10-16 | 2023-10-30 | Pending | High
|  | Develop value proposition statement | Marketing Communications Team | 2023-10-18 | 2023-10-27 | Pending | High
|  | Define key performance indicators (KPIs) | Performance Analytics Team | 2023-10-19 | 2023-10-26 | Pending | Medium
|  | Set budget allocation per channel (digital, print, events) | Finance & Marketing Team | 2023-10-22 | 2023-11-05 | Pending | High
| Phase 3: Content & Creative Development | Content Calendar Creation | Plan monthly content themes and topics | Marketing Content Team | 2023-11-06 | 2023-11-15 | Pending | High
Phase 4: Campaign Execution |  | Launch Digital Advertising Campaigns | Create and deploy Google Ads & Meta Ads | Digital Marketing Team | 2023-11-16 | 2024-01-31 | Pending | High
|  | Phase 5: Monitoring & Reporting | Weekly Performance Review Meetings | Review campaign metrics and KPIs | Marketing Operations Team | 2023-11-20 | Ongoing (Every Monday) | Pending | Medium
|  |  | Phase 6: Optimization & Wrap-Up | Post-Campaign Analysis Report | Compile insights and ROI summary | Marketing Analytics Team | 2024-01-01 | 2024-01-31 | Pending | High
| Phase 7: Future Planning |  |  | Q1 2024 Marketing Roadmap Draft | Begin planning for next quarter initiatives | Marketing Strategy Team | 2023-11-30 | Ongoing (Monthly) | Pending | Medium
|  | Total Project Duration: 14 Weeks (Approx. 3.5 Months) | [6 empty] | Overall Status:Not Started