## Worksheet
Week | Date Range | Marketing Objective | Key Activities | Responsible Team/Person | Status | Budget Allocated (USD) | Expected Results/KPIs
Week 1 | Jan 1 - Jan 7 | Launch Campaign Awareness | Finalize campaign creatives, schedule social media posts, initiate email outreach. | Marketing Team | In Progress | $5,000 | 25% increase in social engagement, 1,500 email opens.
Week 2 | Jan 8 - Jan 14 | Content Distribution & Outreach | Publish blog posts, release video content, run targeted ads. | Content & Digital Team | Completed | $7,500 | 3,000 website visits, 15% increase in follower growth.
Week 3 | Jan 15 - Jan 21 | Customer Engagement & Feedback | Host live Q&A session, collect customer feedback via survey. | Community & CRM Team | In Progress | $1,200 | 500 survey responses, 25% interaction rate during live session.
Week 4 | Jan 22 - Jan 28 | Performance Review & Optimization | Analyze campaign data, adjust ad targeting, optimize content. | Data Analytics Team | In Progress | $2,000 | Improved CTR by 15%, reduced cost per lead by 10%.
Week 5 | Jan 29 - Feb 4 | Scaling Successful Tactics | Increase ad spend on high-performing channels, expand email list. | Digital Marketing Team | In Progress | $10,000 | 25% increase in conversions, target reach of 50K users.
Week 6 | Feb 5 - Feb 11 | Final Reporting & Campaign Wrap-Up | Compile full campaign report, conduct team debrief. | Marketing Manager | Pending | $1,500 | Complete performance analysis document delivered.