## Worksheet
Marketing Planning - Schedule Planner (Manager View)
Task ID | Task Name | Department | Owner | Start Date | End Date | Status | Budget (USD) | KPI Target
001 | Campaign Strategy Development | Marketing | Jane Doe | 2024-03-15 | 2024-03-25 | In Progress | $15,000 | 3.8M Impressions
002 | Content Creation (Q2 Campaign) | Content Team | Mike Chen | 2024-03-18 | 2024-04-15 | In Progress | $35,000 | 1.2M Clicks
003 | Social Media Calendar Launch | Social Media | Sarah Wilson | 2024-03-16 | 2024-04-30 | Completed | $8,500 | 15% Engagement Rate
004 | Influencer Outreach Program | Influencer Marketing | David Kim | 2024-03-17 | 2024-05-15 | Delayed (Pending Approval) | $65,000 | 8.4M Reach
005 | Email Marketing Campaign A/B Testing | Email Team | Lisa Patel | 2024-03-21 | 2024-04-18 | In Progress | $7,500 | 35% Open Rate
006 | Quarterly Performance Review Meeting | Leadership Team | All Managers | 2024-05-13 | 2024-05-13 | Completed | - | None (Internal)
Total Budget Allocated: | [5 empty] | $131,000