## Worksheet
Marketing Planning Schedule Planner
Multi-Page Template for Comprehensive Campaign Management
Phase | Objective | Start Date | End Date | Status | Owner(s)
Market Research & Analysis | Gather insights on target audience and market trends | 2024-01-05 | 2024-01-19 | In Progress | Jane Smith, Mark Lee
Strategy Development | Create campaign strategy and messaging framework | 2024-01-20 | 2024-01-31 | Pending Approval | Jane Smith, Alex Chen
Budget Allocation & Planning | Distribute budget across channels and activities | 2024-02-01 | 2024-02-15 | Pending Review | Lisa Wong, Tom Brown
Content Creation Phase 1 | Develop core visual and copy assets for launch campaign | 2024-02-16 | 2024-03-15 | Pending Start | Sarah Johnson, Carlos Mendez
Pre-Launch Engagement Campaigns | Build anticipation through teaser content and email campaigns | 2024-03-16 | 2024-03-31 | Pending Start | Amanda Kim, Ryan Davis
Campaign Launch Event (Live) | Official launch of product with virtual event and media coverage | 2024-04-01 | 2024-04-03 | Pending Start | All Team Members
Post-Launch Evaluation & Optimization Phase 1 | Analyze initial campaign performance and adjust strategy | 2024-04-04 | 2024-04-15 | Pending Start | Jane Smith, Lisa Wong, Alex Chen
Week | Monday | Tuesday | Wednesday | Thursday | Friday
Week 1 (Jan 5 - Jan 11) | Market Research Kickoff Meeting | Data Collection: Surveys & Interviews | Competitor Analysis Review | Clean & Analyze Survey Data | Report Draft: Key Insights Summary
Week 2 (Jan 12 - Jan 18) | Focus Group Sessions (3 groups) | Data Synthesis & Pattern Identification | Initial Target Audience Persona Development | Review Draft Personas with Leadership | Presentation: Market Insights Report (Internal)
Week 3 (Jan 19 - Jan 25) | <Campaign Strategy Workshop | Define Key Messages & Positioning | Channel Selection & Rationale | Draft Campaign Timeline (Phase 1) | Review Strategy Outline with Stakeholders
Week 4 (Jan 26 - Feb 1) | Budget Workshop: Channel Allocation | Draft Budget Breakdown by Activity | Review Financial Projections | Presentation: Budget Proposal to Finance Team | Finalize Approved Budget & Resources
Week 5 (Feb 2 - Feb 8) | Brief Creative Team on Campaign Vision | Design Concepts for Key Assets (Visuals) | Copywriting Draft: Main Messaging | Creative Review Meeting (Internal) | Pitch: Initial Creative Direction to Leadership
Week 6 (Feb 9 - Feb 15) | Finalize Design Assets & Copy | Review and Approve All Campaign Materials | Campaign Testing: Landing Page, Email Templates | Email List Segmentation & Prep | Final Pre-Launch Check (All Systems)
Role/Team | Main Responsibilities | Key Deliverables | Budget Allocated (USD)
Marketing Director (Jane Smith) | Campaign Vision & Strategy Oversight, Cross-functional Coordination | Approved Campaign Plan, Quarterly Review Reports | $25,000
Market Research Team (Mark Lee) | Data Collection, Analysis & Reporting on Target Audience | Consumer Insights Report, Persona Development | <$12,500
Graphic Design Team (Sarah Johnson) | Visual Concept Creation, Asset Development | 30+ Visual Assets, Brand Guidelines Update | $28,000
Content Writing Team (Carlos Mendez) | Creative Copywriting & Messaging for all platforms | 15+ Unique Copy Pieces, Email Campaigns | $14,500
Digital Marketing Team (Amanda Kim) | <Channel Management: Paid Ads, SEO/SEM Strategy | Google Ads Campaign Setup, Organic Traffic Report | $35,000
Social Media Team (Ryan Davis) | Content Scheduling, Community Engagement & Analytics | 42+ Posts Across Platforms, Engagement Report | $18,500
Event Coordinator (Tom Brown) | Virtual Launch Event Planning & Execution | Live Webinar Setup, Attendee Management Portal | $12,000
Data Analysts (Lisa Wong) | Performance Tracking, KPI Monitoring & Dashboard Creation | Daily/Weekly Performance Dashboards, Optimization Recommendations | $16,500
Total Budget: |  |  | $182,000
KPI Category | Specific Metric | Target Value (30 Days Post-Launch) | Measurement Methodology
Awareness | Total Impressions (All Channels) | 2,500,000+ | Platform Analytics (Google Ads, Meta Insights)
Awareness | Reach (Unique Users) | 1,250,000+ | Campaign-Specific Tracking Pixels & UTM Tags
Engagement | Click-Through Rate (CTR) - Email Campaigns | 4.5% | Email Platform Analytics (Mailchimp)
Engagement | Avg. Time on Site (Website) | >2.5 minutes | Google Analytics 4 Event Tracking
Engagement | Social Media Engagement Rate (Likes, Shares, Comments) | 6.8% | Social Media Platform Insights + Sprout Social Reports
Conversion | Landing Page Conversion Rate | >5.2% | A/B Testing Tools (Optimizely)
Conversion | Lead Generation Count (Form Submissions) | 1,800+ | Campaign Landing Page Analytics
Conversion | Paid Ad Return on Ad Spend (ROAS) | >3.5x | Google Ads & Facebook Pixel Attribution
Retention | Email Open Rate (Monthly Newsletter) | >42% | Mailchimp or HubSpot Platform Reports
Retention | Customer Lifetime Value (CLV) | $380+ | CRM & Sales Data Integration
Risk Category | Potential Risk Event | Impact Level (1-5) | Likelihood (1-5) | Mitigation Strategy
Execution | Delays in Creative Asset Approval | 4 | 3 | Establish clear approval SLAs, assign backup reviewers, use pre-approved templates where possible.
Resources | Talent Shortage (e.g., Designer on Leave) | 4 | 2 | Maintain a roster of freelance contractors; cross-train team members in core skills.
Market | Sudden Change in Competitive Landscape (New Competitor Launch) | 5 | 2 | Maintain competitor monitoring dashboard; conduct bi-weekly competitive analysis reviews.
Technical | Downtime During Virtual Launch Event | 5 | 3 | Hire reliable hosting provider with 99.9% uptime guarantee; conduct full pre-launch technical rehearsal.
Budget | Overrun in Paid Media Spend | 4 | 3 | Set daily spend caps, monitor real-time performance, pause underperforming ad sets immediately.
Communication | Misalignment Between Teams on Messaging Tone/Key Points | 3 | 4 | Hold weekly cross-functional syncs; maintain a shared message center with approved talking points.
High-Risk Items (Impact x Likelihood >= 12):Competitive Shift, Launch Event Downtime
Marketing Planning Schedule Planner – Multi-Page Template ¦ Version: 1.0 ¦ Created: April 5, 2024 ¦ Confidential