## Worksheet
Marketing Planning Schedule Planner
Week / Date | Objective | Activities & Tasks | Responsible Team Member(s) | Status | Budget Allocated (USD)
Week 1 - Jan 01 - Jan 07 | Q1 Campaign Launch Preparation | Finalize campaign concept, create visual assets, finalize messaging strategy | Jane Doe (Marketing Lead) | Pending | $2,500
Week 2 - Jan 08 - Jan 14 | Content Development & Approval | Create social media content, email templates, website banners; review and approve | Mike Chen (Content Team) | In Progress | $3,200
Week 3 - Jan 15 - Jan 21 | Digital Advertising Setup | Launch Google Ads and Meta campaigns, set targeting parameters | Sarah Kim (Digital Marketing) | Pending | $8,000
Week 4 - Jan 22 - Jan 28 | Community Engagement Kickoff | Initiate influencer outreach, schedule social media posts, host live event teaser | Taylor Reed (Social Media) | Pending | $1,500
Week 5 - Jan 29 - Feb 04 | Performance Monitoring & Optimization | Analyze campaign metrics, adjust ad spend and creative elements | David Wong (Analytics) | Pending | $500
Q1 Marketing Summary (Est.)
Total Budget Spent (Projected) |  |  |  |  | $15,700