## Worksheet
Marketing Planning - Schedule Planner (Report Version)
Quarterly Campaign Timeline ¦ Q3 2024 ¦ Prepared on: October 5, 2024
Task ID | Activity / Task Name | Department | Start Date | End Date | Status | Budget (USD)
MKT-01 | Market Research & Analysis | Research & Insights | 2024-07-01 | 2024-07-15 | Completed | $8,500.00
MKT-02 | Target Audience Segmentation | Marketing Strategy | 2024-07-16 | 2024-07-31 | Completed | $6,300.00
MKT-03 | Brand Positioning Development | Branding & Creative | 2024-08-01 | 2024-08-15 | Completed | $9,750.00
MKT-04 | Content Calendar Creation | Content Marketing | 2024-08-16 | 2024-08-31 | In Progress | $5,100.00
MKT-05-M1 | Q3 Campaign Launch (Milestone 1) | Marketing Operations | 2024-09-01 | 2024-09-30 | In Progress | $55,800.00
MKT-11 | Social Media Ads (Phase 1) | Digital Marketing | 2024-09-05 | 2024-10-15 | In Progress | $38,400.00
MKT-12 | Email Campaign Series Launch | Email Marketing | 2024-09-15 | 2024-10-31 | In Progress | $16,950.00
MKT-15-M2 | Mid-Quarter Performance Review (Milestone 2) | Analytics & Reporting | 2024-10-15 | 2024-10-31 | Delayed | $7,800.00
MKT-21 | Customer Feedback Collection & Analysis | Customer Experience | 2024-11-01 | 2024-11-30 | Pending Start | $5,600.00
MKT-25 | Q3 Campaign Post-Mortem & Reporting | Marketing Strategy | 2024-12-01 | 2024-12-15 | Pending Start | $9,350.00