## Worksheet
Marketing Planning Schedule Planner
Small Business Edition ¦ Q3 2024
Marketing Activity | Timeline |  |  |  | Responsible Team | Status
| Start Date | End Date | Frequency | Priority
Q3 Campaign Launch (Social Media) | July 1, 2024 | September 30, 2024 | Weekly Posts + Monthly Contests | High | Social Media Team | In Progress
Email Newsletter Series (3 Emails) | July 5, 2024 | August 10, 2024 | Bi-Weekly (3 emails) | Medium | Email Marketing Team | Scheduled
Influencer Collaboration #1 | July 15, 2024 | August 5, 2024 | One-time Campaign | High | Partnerships Team | Pending Approval
Blogging (Monthly Articles) | July 1, 2024 | September 30, 2024 | One per Month | Medium | Content Team | In Progress
Paid Ads (Google & Facebook) | July 10, 2024 | September 30, 2024 | Daily Budget Optimization | High | Ad Operations Team
Total Activities Scheduled: 5