## Worksheet
Marketing Planning Schedule Planner - Startup
Week | Marketing Objective | Key Activities | Budget (USD) | Status | Owner
Week 1-2 | Launch Product Awareness Campaign | Create social media content, draft email sequence, finalize landing page copy | $1,500 | In Progress | Alice Johnson (Marketing Lead)
Week 3-4 | Drive Initial User Sign-Ups | Promote referral program, run targeted Facebook & Google Ads, host webinar launch | $3,200 | To Do | Mike Chen (Growth Specialist)
Week 5-6 | Generate Early Customer Feedback | Deploy user survey, conduct 1-on-1 interviews, collect testimonials | $800 | To Do | Sarah Patel (Product Marketing)
Week 7-8 | Amplify Social Proof & Trust Signals | Share user stories, publish case studies, update testimonials on site | $1,000 | To Do | Liam Foster (Content Lead)
Week 9-10 | Scale Organic Reach & SEO Growth | Optimize blog content, improve on-page SEO, build backlinks via outreach | $1,200 | To Do | Jessica Lin (SEO Specialist)
Week 11-12 | Prepare for Next Product Update Launch | Analyze campaign performance, plan Q3 marketing roadmap, conduct team retrospective | $500 | To Do | Team Lead (Marketing)