## Worksheet
Marketing Planning Schedule Planner - Team Use
Task/Activity | Owner | Start Date | End Date | Status | Description/Details | Priority | Progress (%)
Market Research & Analysis | Team A | 2024-04-01 | 2024-04-15 | In Progress | Gather customer insights, competitor data, and market trends. | High | 65
Content Creation Plan | Team B | 2024-04-10 | 2024-04-30 | Pending | Develop blog, video, and social media content calendar. | High | 15
Campaign Launch Strategy | Team C | 2024-05-01 | 2024-05-15 | Not Started | Create cross-channel campaign plan and budget allocation. | High | 0
Social Media Scheduling | Team D | 2024-05-16 | 2024-06-30 | Not Started | Distribute content across platforms using scheduling tools. | Medium | 0
KPIs & Performance Tracking Setup | Team E | 2024-05-18 | 2024-06-15 | Not Started | Define KPIs and implement tracking tools (e.g., Google Analytics). | Medium | 0
Monthly Review & Adjustment | Team Lead | 2024-06-15 | 2024-06-30 | Not Started | Analyze performance, update strategy based on data. | Low | 0
Total Tasks: | [6 empty] | 6