## Worksheet
Marketing Planning - Schedule Planner (Tracking View)
Task | Owner | Start Date | End Date | Status | % Complete | Budget (USD)
Market Research & Analysis | Sarah Johnson | 2024-04-01 | 2024-04-15 | Complete | 100% | $8,500
Competitor Benchmarking | James Wilson | 2024-04-16 | 2024-04-30 | In Progress | 65% | $5,750
Brand Messaging Strategy | Maria Garcia | 2024-05-01 | 2024-05-15 | In Progress | 80% | $6,300
Content Creation (Video & Graphics) | David Lee | 2024-05-16 | 2024-06-15 | Delayed | 35% | $18,900
Social Media Campaign Launch | Lisa Chen | 2024-06-16 | 2024-07-31 | Complete | 100% | $15,850
Email Marketing Series | Robert Kim | 2024-07-01 | 2024-07-31 | In Progress | 55% | $7,200
Performance Analytics & Reporting | Sophie Martin | 2024-08-01 | 2024-08-15 | Complete | 100% | $9,550
Post-Campaign Review & Optimization | All Team Members | 2024-08-16 | 2024-08-31 | In Progress | 75% | $4,350
Total Project Cost: | [5 empty] | $81,400
Generated on¦ Tracking View - Marketing Planning Schedule