## Worksheet
Marketing Planning - Quarterly Task Manager
Quarter | Task Name | Owner | Start Date | Due Date | Status | Budget (USD)
Q1: January - March 2024
Q1 | Market Research & Competitor Analysis | Marketing Team Lead | 01/05/2024 | 02/15/2024 | In Progress | $3,500
Q1 | Website Redesign Launch Plan | Web Development Manager | 01/20/2024 | 03/10/2024 | Pending Approval | $15,800
Q2: April - June 2024
Q2 | Social Media Campaign Launch (Spring) | Content Creator | 04/01/2024 | 05/31/2024 | Not Started | $8,750
Q2 | Email Marketing Automation Setup | Digital Marketing Specialist | 04/15/2024 | 06/15/2024 | Not Started | $6,300
Q3: July - September 2024
Q3 | Product Launch Campaign (Summer) | Product Marketing Manager | 07/10/2024 | 09/20/2024 | Not Started | $35,600
Q4: October - December 2024
Q4 | Year-End Holiday Marketing Campaign | Marketing Director | 10/01/2024 | 12/31/2024 | Not Started | $58,900
Total Budget (2024): | [5 empty] | $138,850
Last updated:¦ This template is for quarterly marketing planning and task management.