## Worksheet
Marketing Planning - Time Tracker (Client View)
Project Phase | Task Description | Assigned To | Start Date | End Date | Status | Billed Hours (Est.)(per week)
Planning & Strategy | Client Discovery Workshop & Objective Alignment | Marketing Lead - Sarah Chen | 2024-03-05 | 2024-03-15 | In Progress | 8h/week x 3 weeks = 24h total(est.)
Content Development | Create Brand Messaging & Campaign Copywriting (Social, Email, Web) | Copywriter - James Reed | 2024-03-18 | 2024-04-15 | In Progress | 16h/week x 4 weeks = 64h total(est.)
Design & Creative Production | Visual Identity Refresh (Logo, Templates, Social Graphics) | Designer - Maya Patel | 2024-03-18 | 2024-04-15 | In Progress | 16h/week x 4 weeks = 64h total(est.)
Campaign Execution (Phase 1) | Launch Email & Social Media Campaign (Q2) | Marketing Manager - David Kim | 2024-04-16 | 2024-05-31 | Pending Start | 16h/week x 7 weeks = 112h total(est.)
Reporting & Optimization | Daily Monitoring & Performance Reports (Weekly Review Meetings) | Data Analyst - Lisa Wu | 2024-04-16 | 2024-07-31 | Pending Start | 8h/week x 15 weeks = 120h total(est.)
Total Estimated Billed Hours: | [5 empty] | 384 hours (estimated)
Note:All time estimates are subject to change based on client feedback and project scope adjustments. Weekly updates will be shared every Monday via email.