## Worksheet
Marketing Planning - Time Tracker (Multi-Page)
Task | Start Date | End Date | Status | Hours Spent | Assigned To
Market Research & Analysis | 2025-01-05 | 2025-01-18 | In Progress | 48.5 | Jane Doe
Competitor Benchmarking | 2025-01-19 | 2025-01-30 | Pending | 36.75 | John Smith
KPI Definition & Goals Setting | 2025-01-19 | 2025-01-31 | Pending | 30.25 | Alice Johnson
Create Strategic Timeline | 2025-01-31 | 2025-02-14 | In Progress | 68.75 | Mike Brown
Finalize Marketing Objectives Document | 2025-01-31 | 2025-02-14 | Pending | 45.375 | Sarah Lee
Task | Start Date | End Date | Status | Hours Spent | Assigned To
Campaign Concept Development (Social Media) | 2025-02-15 | 2025-03-14 | In Progress | 86.5 | Jane Doe
Email Marketing Funnel Design | 2025-03-17 | 2025-04-18 | Pending | 64.75 | John Smith
Landing Page Wireframing & UX Review | 2025-03-17 | 2025-04-18 | Pending | 94.67 | Alice Johnson
Budget Allocation & Approval Process | 2025-03-17 | 2025-04-18 | Pending | 56.33 | Mike Brown
Create Content Calendar (Q2) | 2025-04-19 | 2025-04-30 | Pending | 38.96 | Sarah Lee
Task | Start Date | End Date | Status | Hours Spent | Assigned To
Campaign Launch (Social Media & Email) | 2025-05-01 | 2025-05-31 | Pending | 78.43 | Jane Doe
A/B Testing Setup & Optimization | 2025-06-01 | 2025-06-30 | Pending | 74.89 | John Smith
Daily Performance Monitoring (Weekly Reports) | 2025-06-15 | 2025-08-31 | Pending | 49.34 | Alice Johnson
Crisis Response & Feedback Loop Implementation | 2025-06-15 | 2025-08-31 | Pending | 44.71 | Mike Brown
Campaign Post-Mortem & Success Analysis (Q2) | 2025-09-01 | 2025-09-30 | Pending | 67.47 | Sarah Lee