## Worksheet
MARKETING PLANNING - TIME TRACKER (OFFICE USE)
Week | Date Range | Project/Activity | Task Description | Team Member(s) | Status | Budgeted Hours (Est.) | Actual Hours (Logged) | Difference (Hours) | Notes/Remarks
Week 1 | Jan 01 - Jan 07, 2024 | Q1 Campaign Planning | Create campaign strategy and content calendar | Jane Smith, Tom Lee | In Progress | 8 | 6.5 | 1.5 | Content assets in review phase.
Week 2 | Jan 08 - Jan 14, 2024 | Market Research | Competitor analysis and audience segmentation | Emma Davis, James Wang | Completed | 6 | 5.8 | 0.2 | Data compiled and shared with team.
|  | Email Marketing Series | Design and test first email sequence | Anna Clark, Mark Turner | In Review | 4 | 3.2 | 0.8 | A/B testing scheduled for Friday.
Week 3 | Jan 15 - Jan 21, 2024 | Product Launch Prep | Finalize product messaging and launch timeline | Lisa Rodriguez, David Kim | In Progress | 7.5 | 6 | 1.5 | Waiting on product team feedback.
|  | Social Media Content Creation | Produce 3 video assets and 10 static posts | Peter Brown, Sophia Lee | Not Started | 5 | 0 | 5 | To begin after approval.
Week 4 | Jan 22 - Jan 28, 2024 | Launch Campaign Execution | Publish first wave of content across all channels | All Marketing Team | Scheduled | 10 | — | — | Campaign to go live on Jan 23.
TOTAL HOURS: |  |  |  |  | 40.5 | 37.5 | 3 | Tracking ongoing for Q1.