## Worksheet
Week Ending | Marketing Activity | Objective | Time Spent (hrs) | Status | Budget Allocated ($)
Week 1: Planning & Research (Jan 2 - Jan 8)
Jan 8 | Market Research & Competitor Analysis | Understand target audience and competitor positioning | 6.5 | In Progress | 250
Jan 8 | Create Buyer Personas & Journey Maps | Define core customer profiles and touchpoints | 4 | Completed | 100
Week 2: Campaign Strategy (Jan 9 - Jan 15)
Jan 15 | Develop Social Media Content Calendar | Create monthly content plan for platforms | 7 | In Progress | 300
Jan 15 | Set KPIs and Success Metrics for Q1 | Define measurable marketing goals | 3.5 | In Progress | 0
Week 3: Launch Preparation (Jan 16 - Jan 22)
Jan 22 | Design Campaign Creative Assets | Develop visuals and copy for launch | 8 | Pending Approval | 500
Jan 22 | Finalize Email Marketing Sequence | Create onboarding and nurture emails | 5.5 | Completed | 150
Week 4: Campaign Launch & Review (Jan 23 - Jan 29)
Jan 29 | Launch Social Media Campaign | Drive awareness and engagement across platforms | 4 | Launched | 800
Total (4 Weeks) |  |  | 39.5 |  | 2,100.00