## Worksheet
Marketing Planning - Extended To-Do List
Track and manage marketing activities with detailed task information
Task ID | Task Description | Department/Owner | Due Date | Priority | Status | Budget (USD)(Est.)
MT-001 | Develop Q3 Campaign Strategy | Marketing Team | 2024-06-15 | High | Not Started | $8,500(Estimated)($7,200 Used) Notes:Include social media & email components. Dependencies:Market research report (MT-RE-01) must be completed first.
MT-002 | Create Social Media Content Calendar | Social Media Team | 2024-06-28 | Medium
MT-003 | Update Brand Guidelines Document | Brand Management | 2024-07-15
MT-004 | Conduct Competitor Analysis (Q2) | Market Research
MT-005 | Design Landing Page for New Product Launch
MT-006 | Plan and Schedule Email Marketing Campaign
MT-007 | Organize Team Workshop on New Analytics Tools
MT-008 | Publish Blog Series on Industry Trends
MT-009 | Negotiate Sponsorship Deal with Tech Partner
MT-010 | Finalize Event Marketing Plan for Trade Show
Notes:Include digital and onsite promotions. Dependencies:Booth design approved (MT-DES-09).Summary:Total Tasks: 10 ¦ Incomplete: 5 ¦ In Progress: 3 ¦ Complete: 2