## Worksheet
Advanced Gantt Chart - Office Management
Task Name | Start Date | End Date | Duration (Days) | Progress | Status
Project Kickoff & Planning | 2024-04-01 | 2024-04-15 | 15 |  | ⚠️
Office Space Setup | 2024-04-05 | 2024-05-10 | 36 |  | 🟡
IT Infrastructure Deployment | 2024-04-15 | 2024-06-30 | 77 |  | 🟡
Furniture & Equipment Procurement | 2024-05-01 | 2024-06-15 | 46 |  | ✅
Office Move Completion | 2024-06-30 | 2024-06-30 | 1 |  | ✅
Staff Onboarding & Training | 2024-07-01 | 2024-07-31 | 31 |  | 🟡
Facility Management Handover | 2024-07-15 | 2024-08-15 | 31 |  | 🟡
Final System Integration & Testing | 2024-08-01 | 2024-09-15 | 46 |  | ⚠️
Project Completion & Review | 2024-09-30 | 2024-09-30 | 1 |  | ⚠️
Advanced Gantt Chart Template for Office Management - Updated as of April 5, 2024