## Office Management Gantt Chart
Office Management Gantt Chart - Basic Style
Task ID | Task Name | Start Date | End Date | Status | % Complete
001 | Office Setup Planning | 2023-10-01 | 2023-10-15 | In Progress | 75%
002 | Furniture Procurement | 2023-10-16 | 2023-11-05 | In Progress | 55%
003 | IT Infrastructure Installation | 2023-11-06 | 2023-11-25 | Not Started | 0%
004 | Network Security Configuration | 2023-11-26 | 2023-12-10 | Not Started | 0%
005 | Employee Onboarding & Training | 2023-12-11 | 2024-01-31 | Not Started | 0%
M001 | Office Opening Date | 2024-02-01 | 2024-02-01 | Milestone | 100%
Legend:
In Progress: Tasks currently being worked on.
Not Started: Task has not begun yet.