## Worksheet
Office Management Gantt Chart - Business Use
Task ID | Task Name | Start Date | End Date | Status | Assigned To
T001 | Office Relocation Planning | 2024-03-05 | 2024-03-15 | In Progress | Alice Johnson
T002 | IT Infrastructure Setup | 2024-03-16 | 2024-03-31 | In Progress | James Reed
T003 | Furniture Procurement & Delivery | 2024-03-18 | 2024-04-10 | In Progress | Sarah Patel
T004 | Employee Onboarding & Training | 2024-03-25 | 2024-04-15 | In Progress | Maria Lopez
T005 | Office Launch & Final Inspection | 2024-04-18 | 2024-04-19 | Milestone | All Teams
T006 | Post-Launch Review Meeting | 2024-04-21 | 2024-04-21 | Completed | Executive Team