## Worksheet
Task | Owner | Start Date | End Date | Status | Timeline (Weeks)
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 (Forecast)
Project Planning & Kickoff | John Smith | 2023-08-01 | 2023-08-15 | In Progress |  |  |  | 100% | 100%
Design Phase | Sarah Johnson | 2023-08-16 | 2023-09-15 | In Progress |  |  | 100% | 100%
Development Phase | Michael Brown | 2023-09-16 | 2023-11-15 | Delayed |  | 45% | 70% | 95% | Forecast: 12/01
Testing & QA | Lisa Williams | 2023-11-16 | 2023-12-08 | Completed |  | 90% | 100%
Deployment & Training | Daniel Lee | 2023-12-09 | 2024-01-15 | Completed |  | 80% | 100%