## Worksheet
Task Name | Start Date | End Date | Status | Assigned To
Project Kickoff Meeting | 2024-04-05 | 2024-04-05 | In Progress | Jane Doe
Requirement Gathering (Phase 1) | 2024-04-06 | 2024-04-10 | In Progress | John Smith
Design Phase (UI/UX) | 2024-04-11 | 2024-04-18 | Not Started | Sarah Lee
Development Sprint 1 (Core Modules) | 2024-04-19 | 2024-05-03 | Not Started | Mike Johnson
Milestone: System Prototype Complete | 2024-05-03 | 2024-05-03 | Milestone Achieved | Team Lead
Development Sprint 2 (Features & Testing) | 2024-05-04 | 2024-05-17 | Not Started | Amy Chen
Milestone: Beta Release (Internal) | 2024-05-17 | 2024-05-17 | Milestone Achieved | Product Manager
User Acceptance Testing (UAT) | 2024-05-18 | 2024-05-31 | Not Started | Raj Patel
Milestone: Final Release to Production | 2024-06-01 | 2024-06-01 | Milestone Pending | CIO Office
Legend:
Task Row- Regular project task
Milestone- Key achievement date
Status colors indicate progress (In Progress, Not Started, etc.)