## Worksheet
Office Management Gantt Chart - Data Version
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | % Complete | Progress Timeline
001 | Office Space Planning | 2023-10-01 | 2023-10-15 | 14 | In Progress | 65%
002 | Equipment Procurement | 2023-10-16 | 2023-11-05 | 20 | In Progress | 45%
003 | Furniture Installation | 2023-11-06 | 2023-11-15 | 9 | To Do | 0%
004 | Network Setup | 2023-11-16 | 2023-11-25 | 9 | To Do | 0%
005 | Staff Onboarding | 2023-11-26 | 2023-12-10 | 14 | To Do | 0%
006 | Final Review & Approval | 2023-12-11 | 2023-12-15 | 4 | To Do | 0%
Total Duration: |  |  |  |  | 37 days