## Worksheet
Office Management Gantt Chart - Detailed View
Task ID | Task Name / Description | Timeline (Weeks)
|  | Week 1 Jan 1 - Jan 7 | Week 2 Jan 8 - Jan 14 | Week 3 Jan 15 - Jan 21 | Week 4 Jan 22 - Jan 28 | Week 5 Jan 29 - Feb 4 | Week 6 Feb 5 - Feb 11 | Week 7 Feb 12 - Feb 18 | Week 8 Feb 19 - Feb 25
TM-001 | Office Space Planning & Design
TM-002 | IT Infrastructure Setup
TM-003 | Furniture Procurement
TM-004 | Employee Onboarding Process Design
TM-005 | Security System Installation
TM-006 | Facility Inspection & Compliance Check
MS-01 | Project Kickoff - Office Setup Initiated
MS-02 | Furniture Delivery Confirmation
MS-03 | Full Office Readiness - Go Live
TM-007 | Final Staff Training & Orientation
TM-008 | IT System Integration & Testing
Total Duration |  | 8 Weeks (Jan 1 - Feb 25)
Legend:Progress bars indicate task completion percentage. Milestones highlight critical project events.