## Worksheet
Office Management - Freelancer Gantt Chart
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Progress(% Complete)
T001 | Project Planning & Scope Definition | 2024-03-25 | 2024-03-31 | 7 | Completed
T002 | Resource Allocation & Team Assignment | 2024-04-01 | 2024-04-15 | 15 | In Progress
T003 | Design Phase - UX/UI Mockups | 2024-04-16 | 2024-05-15 | 30 | In Progress
T004 | Development - Frontend Implementation | 2024-05-16 | 2024-06-30 | 45 | Pending
T005 | Development - Backend Integration | 2024-06-01 | 2024-07-31 | 61 | Pending
T006 | Testing & QA Cycle | 2024-08-01 | 2024-08-31 | 31 | Pending
T007 | Final Review & Client Feedback | 2024-09-01 | 2024-09-15 | 15 | Pending
T008 | Deployment & Go-Live | 2024-09-16 | 2024-09-30 | 15 | Pending