## Worksheet
Task ID | Task Name | Start Date | End Date | Status | Assigned To | Timeline (Weeks)
001 | Project Initiation | 2023-10-02 | 2023-10-06 | In Progress | Alice Johnson | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | ✅
002 | Resource Planning | 2023-10-09 | 2023-10-13 | In Progress | Bob Smith | Wk 1 | Wk 2 | Wk 3 | Wk 4 | 🟡
003 | Office Setup | 2023-10-16 | 2023-10-27 | Pending | Carol Lee | Wk 1 | Wk 2 | Wk 3 | 🔴
004 | IT Infrastructure Deployment | 2023-10-16 | 2023-11-03 | In Progress | Dave Brown | Wk 4 | Wk 5 | Wk 6 | ✅
005 | Team Onboarding | 2023-11-06 | 2023-11-17 | Not Started | Eva Green | Wk 7 | Wk 8 | Wk 9
Task ID | Task Name | Start Date | End Date | Status | Timeline (Weeks)
006 | Facility Inspection | 2023-11-20 | 2023-11-30 | Status | Wk 9 | Wk 10 | Wk 11
007 | Security System Installation | 2023-12-04 | 2023-12-15 | Status | Wk 10 | Wk 11 | —
008 | Final Audit & Handover | 2023-12-18 | 2023-12-29 | Status | Wk 11 | Wk 12
Project Summary & Key Milestones
Project Start |  | 2023-10-02
Resource Planning Complete |  | 2023-10-13
Office Setup Complete |  | 2023-10-27
IT Infrastructure Live |  | 2023-11-03
Team Fully Onboarded |  | 2023-11-17
Project Completion |  | 2023-12-29
Legend & Color Code
✅ In Progress / Completed |  | Task is active or completed.
🟡 On Hold / In Progress |  | Task is delayed or partially completed.
🔴 Not Started |  | Task has not yet begun.
— No Activity |  | Task is not active during this period.