## Worksheet
Office Management Gantt Chart
Period:January 2024 - December 2024 ¦Status:Active
Task Name | Start Date | End Date | Assigned To | Progress (Duration)
Office Renovation Planning | 01-Jan-2024 | 15-Feb-2024 | Jane Smith | 95%
HVAC System Upgrade | 01-Mar-2024 | 30-Apr-2024 | Mike Johnson | 70%
IT Infrastructure Upgrade | 15-Mar-2024 | 15-Jun-2024 | David Lee | 50%
Furniture Procurement | 20-Mar-2024 | 15-May-2024 | Sarah Williams | 85%
Employee Onboarding | 01-Apr-2024 | 30-Jun-2024 | Emma Brown | 40%
Office Move Day | 15-Jul-2024 | 15-Jul-2024 | N/A | Complete
Post-Move Evaluation | 01-Aug-2024 | 31-Aug-2024 | Lisa White | 15%
Q3 Facilities Audit | 01-Sep-2024 | 30-Sep-2024 | Ryan Hall | 0%
Printed on:document.write(new Date().toLocaleDateString());
This document is for internal office management use only.