## Office Management - Gantt Chart
Office Management - Gantt Chart
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Progress
T001 | Office Space Setup | 2024-03-15 | 2024-03-31 | 17 | In Progress
T002 | IT Infrastructure Installation | 2024-03-18 | 2024-04-15 | 39 | In Progress
T003 | Hiring and Onboarding Team | 2024-03-25 | 2024-04-30 | 36 | In Progress
T004 | Office Equipment Procurement | 2024-03-16 | 2024-03-29 | 14 | In Progress
T005 | Internal Training Program | 2024-04-16 | 2024-05-17 | 32 | Pending
T006 | Office Launch Event | 2024-05-18 | 2024-05-18 | 1 | Pending
Legend:In Progress ¦ Pending ¦ Completed
Status colors reflect current task stage. Progress bar indicates percentage completion.